## Dashboard
AERS TRANSFORM v2.0 ¦ 16-WEEK MASTER CONTROL
Current regenerated content, developer handover and launch-readiness view ¦ As of 17 September 2026
Programme KPI | Current value | Control Gate | Owner | Status
Programme weeks | 16 | Weeks 1–2 source alignment | Programme Owner | Open
Capability modules | 6 | Modules 1–6 file lock | Content Owner | Passed
Regenerated module masters | 6 | Week 15 demonstration pack | Assessment Lead | Passed
Final-stage packs | 2 | Week 16 closure pack | Programme Owner | Passed
Current controlled files | 10 | Developer ingestion mapping | Product / Developer | Open
Weeks cleared as current | 14 | Platform workflow UAT | QA Lead | Open
Weeks needing alignment review | 2 | ERI method approval | Authorised AERS Reviewer | Open
Overall content-control status | Ready with Weeks 1–2 alignment review | Passport release UAT | Programme Owner / QA | Open
GO / NO-GO PRINCIPLE
Content regeneration is complete for Modules 1–6 and Weeks 15–16. The programme must not be declared platform-launch ready until Weeks 1–2 are aligned, every file is ingested and QA-tested, human-review permissions work, and the ERI/Passport approval rules are formally authorised.

## 16-Week Map
AERS TRANSFORM v2.0 ¦ APPROVED 16-WEEK IMPLEMENTATION MAP
Weeks 1–2 assess and personalise ¦ Weeks 3–14 six sequential modules ¦ Week 15 demonstrate ¦ Week 16 decide and progress
Week | Phase / Module | Weekly focus | Platform learning | Guided session | Mandatory evidence / output | Quiz gate | Human-review gate | Progression decision | Primary controlled file | Developer action | File control status
1 | Assess and Personalise | Orientation, profile, consent and baseline assessment | Onboarding, responsible use and baseline instruments | Orientation and platform walkthrough | Consent, learner profile and baseline record | As applicable | Human check for consent, completeness and exceptions | Baseline completed or action required | Existing Week 1 pack to reconcile | Configure onboarding, consent, roles and baseline workflow | Alignment Review
2 | Assess and Personalise | Baseline interpretation and personalised pathway | Results explanation, self-awareness and priority selection | Results and goal-setting session | Approved personalised pathway and priority record | As applicable | Human approval of pathway and exceptions | Pathway approved or action required | Existing Week 2 pack to reconcile | Configure pathway, priorities and learner acknowledgement | Alignment Review
3 | Module 1 Career Clarity | Career Clarity I | Lessons 1–2, notes, quiz and practice | 60-minute exploration and mapping session | Career research, interest and strength evidence | 60% | Each compulsory evidence item 6/10 | Module active | AERS_Transform_Module_1_Career_Clarity_Content_Master_v2.0.docx | Release Module 1 learning, quiz, evidence and review workflow | Current and Verified
4 | Module 1 Career Clarity | Career Clarity II and module closure | Lessons 3–4, action planning and evidence revision | 60-minute evidence review and closure session | Verified Career Direction Plan and portfolio | 60% | Each compulsory evidence item 6/10; revisions complete | Verified / conditional action / intervention | AERS_Transform_Module_1_Career_Clarity_Content_Master_v2.0.docx | Apply module-close decision and unlock rules | Current and Verified
5 | Module 2 Resume Readiness | Résumé Readiness I | Lessons 1–2, evidence inventory and résumé draft | 60-minute résumé workshop | Résumé Version 1 and claim-to-evidence map | 60% | Each compulsory evidence item 6/10 | Module active | AERS_Transform_Module_2_Resume_Readiness_Content_Master_v2.0.docx | Release Module 2 after Module 1 close | Current and Verified
6 | Module 2 Resume Readiness | Résumé Readiness II and module closure | Lessons 3–4, profile and revision | 60-minute review and correction clinic | Verified Résumé Portfolio Version 2 | 60% | Each compulsory evidence item 6/10; revisions complete | Verified / conditional action / intervention | AERS_Transform_Module_2_Resume_Readiness_Content_Master_v2.0.docx | Store versions and verified résumé status | Current and Verified
7 | Module 3 Communication | Communication Readiness I | Lessons 1–2, introduction, speaking and listening | 60-minute speaking and listening session | Introduction recording and workplace response | 60% | Each compulsory evidence item 6/10 | Module active | AERS_Transform_Module_3_Communication_Readiness_Content_Master_v2.0.docx | Enable recording, evidence and rubric workflow | Current and Verified
8 | Module 3 Communication | Communication Readiness II and module closure | Lessons 3–4, channels, discussion and presentation | 60-minute presentation and evidence review | Verified Communication Evidence Portfolio Version 2 | 60% | Each compulsory evidence item 6/10; revisions complete | Verified / conditional action / intervention | AERS_Transform_Module_3_Communication_Readiness_Content_Master_v2.0.docx | Close module and preserve reviewed evidence | Current and Verified
9 | Module 4 Aptitude | Aptitude Readiness I | Diagnostic, methods and practice | 60-minute diagnostic and error-review session | Diagnostic record, worked methods and error log | 60% | Each compulsory evidence item 6/10 | Module active | AERS_Transform_Module_4_Aptitude_Readiness_Content_Master_v2.0.docx | Configure timed work, attempts and evidence | Current and Verified
10 | Module 4 Aptitude | Aptitude Readiness II and module closure | Practice, reasoning and improvement verification | 60-minute problem-solving review | Verified Aptitude Evidence Portfolio Version 2 | 60% | Each compulsory evidence item 6/10; revisions complete | Verified / conditional action / intervention | AERS_Transform_Module_4_Aptitude_Readiness_Content_Master_v2.0.docx | Store attempt history and human verification | Current and Verified
11 | Module 5 Workplace Readiness | Workplace Readiness I | Professional behaviour, communication and scenarios | 60-minute scenario-practice session | Professional email or scenario-response evidence | 60% | Each compulsory evidence item 6/10 | Module active | AERS_Transform_Module_5_Workplace_Readiness_Content_Master_v2.0.docx | Enable scenario submission and review | Current and Verified
12 | Module 5 Workplace Readiness | Workplace Readiness II and module closure | Teamwork, ownership, judgement and action planning | 60-minute evidence review and closure | Verified Workplace Readiness Portfolio Version 2 | 60% | Each compulsory evidence item 6/10; revisions complete | Verified / conditional action / intervention | AERS_Transform_Module_5_Workplace_Readiness_Content_Master_v2.0.docx | Apply human close decision and audit trail | Current and Verified
13 | Module 6 Interview Readiness | Interview Readiness I | Preparation, résumé discussion, HR and behavioural answers | 60-minute preparation and answer-practice session | Research sheet, STAR bank and response recording | 60% | Each compulsory evidence item 6/10 | Module active | AERS_Transform_Module_6_Interview_Readiness_Content_Master_v2.0.docx | Enable recording, preparation and reviewer tools | Current and Verified
14 | Module 6 Interview Readiness | Interview Readiness II and module closure | Role-specific reasoning and human-led mock interview | 60-minute mock interview and feedback session | Verified Interview Readiness Portfolio Version 2 | 60% | Each compulsory evidence item 6/10; revisions complete | Verified / conditional action / intervention | AERS_Transform_Module_6_Interview_Readiness_Content_Master_v2.0.docx | Capture human mock-interview decision and correction | Current and Verified
15 | Demonstrate | Final demonstration and targeted reassessment | Evidence consolidation and final preparation | Panel interview and employer simulation | Final interview rubric, panel notes, simulation, reflection and reassessment record | No new module quiz | Human panel, moderation and comparable reassessment | Complete / continuing development / re-attempt / hold | AERS_Transform_Week_15_Final_Demonstration_and_Reassessment_Pack_v2.0.docx | Configure eligibility, panel, moderation and Week 16 handover | Current and Verified
16 | Decide and Progress | Final ERI, Passport and progression | ERI interpretation, Passport validation and portfolio closure | Final evidence conference and planning | Approved ERI Profile, Passport, portfolio and 30/60/90-day plan | Not applicable | Authorised reviewer approval mandatory | Completed / continuing development / conditional / hold | AERS_Transform_Week_16_Final_ERI_Employability_Passport_and_Progression_Plan_Pack_v2.0.docx | Generate draft only; human approval before Passport release | Current and Verified

## Deliverable Register
AERS TRANSFORM v2.0 ¦ CONTROLLED DELIVERABLE REGISTER
One current source per deliverable ¦ Older versions remain archive-only and must not be published
ID | Category | Weeks | Deliverable | Current filename | Content scope | Control status | Owner | Developer use | Next action
D01 | Foundation | 1 | Week 1 onboarding, consent and baseline pack | Existing source to identify and align | Onboarding, consent, learner profile and baseline | Alignment Review | Programme Owner | Onboarding and baseline configuration | Confirm current source and issue v2.0
D02 | Foundation | 2 | Week 2 results and personalised pathway pack | Existing source to identify and align | Baseline interpretation, priorities and pathway approval | Alignment Review | Programme Owner | Personalisation and pathway configuration | Confirm current source and issue v2.0
D03 | Module Master | 3–4 | Module 1 Career Clarity | AERS_Transform_Module_1_Career_Clarity_Content_Master_v2.0.docx | Bilingual scripts, notes, quizzes, activities, evidence, review and plan | Regenerated and Verified | Content Owner | Content ingestion and module gate | Lock checksum and map content objects
D04 | Module Master | 5–6 | Module 2 Résumé Readiness | AERS_Transform_Module_2_Resume_Readiness_Content_Master_v2.0.docx | Bilingual scripts, notes, quizzes, résumé evidence and review | Regenerated and Verified | Content Owner | Content ingestion and module gate | Lock checksum and map content objects
D05 | Module Master | 7–8 | Module 3 Communication Readiness | AERS_Transform_Module_3_Communication_Readiness_Content_Master_v2.0.docx | Bilingual scripts, notes, quizzes, recordings, activities and review | Regenerated and Verified | Content Owner | Content ingestion and media/evidence workflow | Lock checksum and map content objects
D06 | Module Master | 9–10 | Module 4 Aptitude Readiness | AERS_Transform_Module_4_Aptitude_Readiness_Content_Master_v2.0.docx | Bilingual learning, quizzes, practice, evidence and human review | Regenerated and Verified | Assessment Lead | Assessment, attempt and evidence workflow | Lock checksum and map content objects
D07 | Module Master | 11–12 | Module 5 Workplace Readiness | AERS_Transform_Module_5_Workplace_Readiness_Content_Master_v2.0.docx | Bilingual learning, scenarios, evidence, review and action plan | Regenerated and Verified | Content Owner | Scenario and human-review workflow | Lock checksum and map content objects
D08 | Module Master | 13–14 | Module 6 Interview Readiness | AERS_Transform_Module_6_Interview_Readiness_Content_Master_v2.0.docx | Four bilingual lessons, 40 quiz questions, evidence and mock interview | Regenerated and Verified | Assessment Lead | Recording, mock interview and correction workflow | Lock checksum and map content objects
D09 | Final Stage | 15 | Final Demonstration and Reassessment | AERS_Transform_Week_15_Final_Demonstration_and_Reassessment_Pack_v2.0.docx | Six-module consolidation, panel, simulation, reflection and reassessment | Regenerated and Verified | Assessment Lead | Eligibility, panel, moderation and handover | Configure controlled workflow and UAT
D10 | Final Stage | 16 | Final ERI Passport and Progression | AERS_Transform_Week_16_Final_ERI_Employability_Passport_and_Progression_Plan_Pack_v2.0.docx | Seven-domain ERI, Passport, portfolio, conference and progression plan | Regenerated and Verified | Programme Owner | Draft generation, approval and release | Approve ERI method and complete release UAT

## Developer Matrix
AERS TRANSFORM v2.0 ¦ DEVELOPER INGESTION AND ACCEPTANCE MATRIX
The system supports delivery and evidence flow; authorised humans retain assessment, ERI and Passport authority
Workflow | Required platform behaviour | Learner action | Human action | System output | Hard control | UAT evidence | Owner | Status
Onboarding and consent | Role-based onboarding, consent versioning and cohort isolation | Activate account and consent | Resolve exceptions | Timestamped profile and consent | No participation without required consent | Valid and exception journeys | Product / QA | Open
Baseline and pathway | Deliver approved assessment and show interpretable results | Complete baseline and confirm goals | Approve pathway and support | Baseline profile and personalised journey | No unsupported automated readiness decision | Assessment and pathway UAT | Assessment Lead | Open
Sequential module release | Unlock only the approved next module | Complete current module | Approve close or intervention | Next-action state | No bypass of module gate | All gate branches tested | Product Owner | Open
Learning and quiz | Track video/note access, quiz score and attempts | Learn and attempt quiz | Support where required | Completion and score | Quiz pass is 60%; quiz alone never verifies capability | Pass, fail and retry cases | Developer / QA | Open
Evidence submission | Store file, version, timestamp, declaration and metadata | Submit authentic evidence | Check completeness | Versioned submission | No overwriting prior versions | Upload and version-history UAT | Developer / QA | Open
Human rubric review | Present approved rubric and evidence context | View feedback | Score, comment and decide | Auditable human decision | Every compulsory evidence item minimum 6/10; holds can override score | Review, revision and hold cases | Assessment Lead | Open
Revision and resubmission | Return specific feedback and link resubmission | Correct and resubmit | Re-review and verify | Linked evidence versions | Original record retained | Multi-version UAT | Developer / QA | Open
Guided sessions | Schedule, record attendance and link outputs | Attend and practise | Facilitate and record observations | Session record | One 60-minute session weekly from Week 3 | Session and absence cases | Facilitator Lead | Open
Week 15 demonstration | Manage eligibility, panel, independent scores and moderation | Complete final demonstration | Panel assesses and reviewer moderates | Final readiness evidence | Comparable reassessment only when authorised | Panel and reassessment UAT | Assessment Lead | Open
ERI profile | Calculate/display only approved versioned method | Review profile | Interpret, moderate and approve | Draft or approved ERI profile | No invented or unapproved numeric ERI | Method-version and approval UAT | Programme Owner | Open
Employability Passport | Generate draft from approved claims and evidence | Validate identity and sharing | Approve correction and release | Versioned Passport | No automatic issuance | Draft, correction, withhold and release UAT | Programme Owner / QA | Open
Audit and security | Preserve decisions, access, versions and change history | Access own records only | Access authorised cohorts and decisions | Audit trail and alerts | Institution/cohort isolation and least privilege | Permission and audit tests | Technical Lead | Open

## Controls
AERS TRANSFORM v2.0 ¦ APPROVED CONTROL VALUES
Use these values for content configuration, reviewer workflow and UAT; changes require controlled approval
Control ID | Area | Approved rule | System implementation | Authority | Change status
C01 | Quiz | Pass at 60% or above; approved attempt rules; no negative marking unless separately approved | Calculate and display; retain attempts | Programme / Assessment Owner | Locked
C02 | Human evidence | Each compulsory human-reviewed evidence item must score at least 6/10 | Block module close until decision and required correction | Authorised reviewer | Locked
C03 | Module gate | No separate 7/10 module gate | Do not configure an additional aggregate gate | Programme Owner | Locked
C04 | Completion | All compulsory evidence verified, revisions complete and feedback acknowledged | Gate next module on all conditions | Authorised reviewer | Locked
C05 | Guided session | One 60-minute guided session weekly from Week 3 | Schedule, attendance, outputs and notes | Facilitator Lead | Locked
C06 | Responsible AI | Material assistance declared; no fabrication, impersonation or undisclosed live answers | Declaration, reviewer flag and audit record | Assessment Lead | Locked
C07 | Decision statuses | Submitted, Under Review, Verified, Verified with Revision, Evidence Pending, Rejected, Hold or Escalation | Controlled state machine with reason and timestamp | Programme Owner | Locked
C08 | Public Passport labels | Verified, Developing, Evidence Pending | Only approved claims and public labels exposed | Authorised AERS reviewer | Locked
C09 | ERI | Numeric value only with an approved, versioned method | Keep draft hidden until human approval | Programme Owner / Moderator | Governance Approval
C10 | Passport | Human approval required before issuance or external sharing | Draft, validate, correct, approve, release and revoke/version | Authorised AERS reviewer | Locked
C11 | Privacy | Role, institution and cohort access isolation; consent and sharing scope retained | Least privilege, audit, secure links and retention controls | Data / Programme Owner | Governance Approval
C12 | Programme claim | No degree, licence, job offer or employment guarantee | Display approved disclaimer in final outputs | Programme Owner | Locked

## Audit
AERS TRANSFORM v2.0 ¦ MASTER INDEX AUDIT
Terminal checks only ¦ Resolve failures before developer handover or publication
Check | Expected | Actual | Result | Owner | Action
16 programme weeks | 16 | 16 | PASS | Programme Owner
Six controlled module masters | 6 | 6 | PASS | Programme Owner
Current and verified weeks | 14 | 14 | PASS | Content Owner
Alignment review weeks | 2 | 2 | PASS | Programme Owner | Issue or align Weeks 1–2 v2.0
Controlled deliverables | 10 | 10 | PASS | Content Owner
Regenerated and verified deliverables | 8 | 8 | PASS | Content Owner
Developer workflows | 12 | 12 | PASS | Product Owner
Approved controls | 12 | 12 | PASS | Programme Owner